THE ADVANTAGE SERVICES

━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━

TICKET MIGRATION FRAMEWORK  —  BORDIO TO HUBSTAFF

2-Week Hybrid Migration Structure  |  Repetitive · One-Time · Temporary

| COMPANY | The Advantage Services | PROJECT MGR | Abdul Rafaay |
| --- | --- | --- | --- |
| SOURCE | Bordio | TARGET | Hubstaff |
| TIMELINE | 2 Weeks ¦ June 2026 | REPORT TO | Hendrick Alves |

HOW THIS FRAMEWORK WORKS

This is a clean hybrid migration structure built for a 2-week window. It takes every ticket from Bordio and moves it into Hubstaff in an organised, trackable way. Tickets are grouped into three types first — then each type follows a simple 4-phase journey from Review all the way to Live. The same structure can be applied to any other platform or workflow migration in the future with minimal changes.

The 4-Phase Migration Journey

| PHASE 1 | PHASE 2 | PHASE 3 | PHASE 4 |
| --- | --- | --- | --- |
| REVIEW Days 1–3 | MOVE Days 4–8 | CHECK Days 9–11 | CLOSE Days 12–14 |
| Audit all Bordio tickets. Categorise every ticket by type. Build Hubstaff workspace. | Migrate tickets in priority order. Recreate in Hubstaff. Assign to right people. | Verify every ticket moved correctly. Get developer confirmations. Fix any errors. | Freeze Bordio. Hubstaff goes live as the only active system. Final report submitted. |

THREE TICKET TYPES — BORDIO TO HUBSTAFF

Every ticket in Bordio belongs to one of these three types. The type determines how it is migrated, how it is set up in Hubstaff, and what happens to it after migration.

| TICKET TYPE | WHAT IT MEANS | BORDIO EXAMPLES | HOW IT MOVES | HUBSTAFF SETUP |
| --- | --- | --- | --- | --- |
| REPETITIVE | A task that happens again and again for the same client — same job, new period. | Monthly Reports to MFK · Noom monthly transactions · Bank statements · Payroll inquiries | Current open cycle only. Past cycles archived. | Set as a recurring task with monthly/weekly reset. |
| ONE-TIME | A task for a new client or a unique job that only happens once and closes when done. | Generate invoice DUNCAN · File Declaration IB 2024 · Levenstestament · Extension Payment Plan | Migrate fully with all sub-tasks and attachments. | Standard task under client project. Close on completion. |
| TEMPORARY | A short-life task — a meeting, quick review, or one-off action with a clear end point. | Meeting with Tshepho · Review BDC account · Group Funds Transfer to TAS | Open ones migrate. Completed ones go to archive only. | Hard due date set. Auto-archived on completion. |

2-WEEK MIGRATION PLAN — WEEK BY WEEK

WEEK 1 — Review, Setup & Move  (Days 1–7)

| DAYS | PHASE | WHAT HAPPENS | WHO |
| --- | --- | --- | --- |
| 1–2 | REVIEW | Log in to Bordio and go through every single ticket. Write down the ticket name, client, current status, and type (Repetitive / One-Time / Temporary) in the Migration Tracker. Do not move anything yet — this is a full read-through only. | Data Entry + PM |
| 2 | REVIEW | PM reviews the completed tracker, confirms all tickets are captured and correctly typed, and gives sign-off to begin moving tickets. | PM — Abdul Rafaay |
| 3 | REVIEW | Build the Hubstaff workspace: create all client projects, task sections, and invite all team members with correct roles. Mirror the Bordio structure as closely as possible. | PM — Abdul Rafaay |
| 4–5 | MOVE | Begin migrating tickets — start with the most urgent first. Repetitive: migrate current active cycle only. One-Time: migrate fully with sub-tasks. Temporary: migrate only those still open. Copy title, description, priority, due date, and assignee exactly. | Data Entry Person |
| 5 | MOVE | For every ticket moved: update the tracker row immediately with the new Hubstaff task ID and mark as Migrated. Do not wait until end of day. | Data Entry Person |
| 6–7 | MOVE | Continue migrating remaining tickets — backlog and lower-priority items. Complete all three ticket types by end of Day 7. PM does a daily spot-check on 20% of moved tickets. | Data Entry + PM |

WEEK 2 — Check, Fix & Close  (Days 8–14)

| DAYS | PHASE | WHAT HAPPENS | WHO |
| --- | --- | --- | --- |
| 8–9 | CHECK | PM and Data Entry Person go through every migrated ticket side-by-side. Check 5 things per ticket: correct title, full description, right priority, correct due date, correct assignee. Any issue gets flagged and fixed the same day. | Data Entry + PM |
| 9 | CHECK | PM sends a message to every developer: 'Please review your tasks in Hubstaff and confirm they look right.' Collect their confirmation before moving forward. | PM — Abdul Rafaay |
| 10 | CHECK | Fix all issues raised — missing descriptions, wrong assignees, incorrect priorities. Re-check fixed tickets once more before marking Verified in the tracker. | Data Entry Person |
| 11 | CLOSE | PM confirms zero unresolved issues remain. Total ticket count in Hubstaff must match the original Bordio count exactly — no ticket left behind. | PM — Abdul Rafaay |
| 12 | CLOSE | Formally stop all Bordio activity. Notify the entire team: Hubstaff is now the only active system. Bordio remains open as a read-only archive — nothing new is added. | PM — Abdul Rafaay |
| 13–14 | CLOSE | PM submits the final migration completion report to Hendrick Alves. Hubstaff is fully live. Migration declared complete. | PM — Abdul Rafaay |

HOW EACH TICKET TYPE IS HANDLED DURING THE MOVE

| TICKET TYPE | WHAT TO COPY FROM BORDIO | HOW TO SET IT UP IN HUBSTAFF | AFTER MIGRATION |
| --- | --- | --- | --- |
| REPETITIVE | Title · Description · Assignee · Due date (current cycle only) · Any active notes or comments | Create as recurring task. Set the correct repeat interval (monthly/weekly). Place under the right client project. | Add a note: 'Previous cycles completed in Bordio — archived.' Developer confirms task is correct. |
| ONE-TIME | Title · Full description · All sub-tasks · Priority · Due date · Assignee · Attachments | Create as a standard task under the client's project. Recreate each sub-task individually. Re-upload all files. | Task closes when the job is done. PM marks complete and notifies the relevant client-facing team member. |
| TEMPORARY | Title · Description · Due date · Assignee. Check if still open or already done before migrating. | Create under a 'Temporary Tasks' section in the relevant project. Add the label TEMP. Set a hard due date. | Archive immediately on completion. Any temp task open past its due date is escalated to PM within 24 hours. |

MIGRATION TRACKER — WHAT TO LOG FOR EVERY TICKET

One row per ticket. Fill every column as you go. The PM reviews this tracker every morning.

| # | TICKET | CLIENT | TYPE | STATUS (BORDIO) | PRIORITY | MIGRATED | VERIFIED | NOTES |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Monthly Reports to MFK | MFK | Repetitive | Open | Medium | — | — | — |
| 2 | Bank Statements – Request | Various | Repetitive | Open | — | — | — | — |
| 3 | Noom – Monthly Transaction | Noom | Repetitive | Open | Medium | — | — | — |
| 4 | Demand Letter Taxes 2021/22 | Client | One-Time | In Progress | High | — | — | — |
| 5 | Extension Payment Plan / Tax | Client | One-Time | In Progress | Critical | — | — | — |
| 6 | File Declaration – IB 2024 | Client | One-Time | Awaiting | Low | — | — | — |
| 7 | Generate Invoice – DUNCAN Jonathan | DUNCAN | One-Time | New Task | Medium | — | — | — |
| 8 | Levenstestament | Client | One-Time | In Progress | High | — | — | — |
| 9 | Pointers – NOOM Charges | Noom | One-Time | In Progress | Low | — | — | — |
| 10 | Meeting – Tshepho Agreement | Internal | Temporary | In Progress | Low | — | — | — |
| 11 | Review BDC Account 171379 | BDC | Temporary | New Task | High | — | — | — |
| 12 | Group Funds Transfer – TAS | TAS | Temporary | In Progress | Low | — | — | — |

SIMPLE RULES — FOR EVERYONE ON THIS MIGRATION

| # | DATA ENTRY PERSON — MUST DO | PROJECT MANAGER — MUST DO |
| --- | --- | --- |
| 1 | Read every Bordio ticket fully before migrating — never skim. | Review and approve the tracker before any tickets are moved. |
| 2 | Copy the title exactly. Never rephrase or shorten it. | Do a daily spot-check on at least 20% of tickets moved that day. |
| 3 | Update the tracker immediately after each ticket — never batch at end of day. | Collect written confirmation from every developer by Day 9. |
| 4 | If something is unclear — stop and ask the PM. Never guess. | Escalate any unresolved issue to Hendrick Alves within 24 hours. |
| 5 | Never delete anything from Bordio. It stays as the archive. | Submit daily progress update to Hendrick Alves every evening. |
| 6 | Flag any ticket with missing info in the tracker Notes column immediately. | Declare migration complete only when tracker shows 100% Verified. |

| Prepared By Abdul Rafaay Project Manager — The Advantage Services Migration Period: June 2026 | Reviewed By Hendrick Alves Reporting Manager — The Advantage Services Approval Date: _______________ |
| --- | --- |

Draft — Flexible & Adaptable  |  Confidential — Internal Use Only